## RFB
Request for Bids
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Prequalification (Y/N) | Procurement Process | Evaluation Options | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Pre-qualification Documents |  | Specific Procurement Notice |  | Amendments to Pre-qualification Documents | Opening / Minutes of Pre-qualification |  | Pre-qualification Evaluation Report |  | Draft Bidding Documents |  | Specific Procurement Notice |  | Invitation to Providers |  | Amendments to Bidding Documents | Bid Submission / Opening / Minutes |  | Bid Evaluation Report and Recommendation for Award |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[14 empty] | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BEEP-P143580-NCB-29-W-15-FBIH / Works for implementation of energy efficiency measures for University of Clinical Center Sarajevo (Department of Orthopedic and Trauma) | No | IDA-53930,IDA-55380 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Works | Open - National | N | Single Stage One Envelope |  |  |  | Signed | Cleared | [19 empty] | 2015/07/08 |  |  |  | 2016/01/07
BEEPAF-P165405-RFB-12-W-21-FBIH / Works on reconstruction of objects: LOT 1: Poliklinika za plućne bolesti "Podhrastovi, LOT 2: UKCS Klinika za urgentnu medicinu Sarajevo, LOT 3: UKCS Klinika za fizikalnu medicinu i rehabilitaciju Sarajevo | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Works (without prequalification) SPD | Signed | Cleared | [9 empty] | 2021/09/10 | 2021/10/01 | 2021/09/15 |  |  |  |  | 2021/10/15 | 2021/10/29 | 2021/10/29 | 2021/11/29 | 2021/11/12 | 2021/12/29 | 2021/11/17 | 2022/01/10 | 2022/07/27 | 2022/03/17
BEEPAF-165405-RFB-10-W-21-FBIH / Works on reconstruction of 5 objects in ZE-DO canton | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Works (without prequalification) SPD | Signed | Cleared | [9 empty] | 2021/06/17 | 2021/06/23 | 2021/06/22 | 2021/06/23 |  |  |  | 2021/07/22 | 2021/07/21 | 2021/08/01 | 2021/09/03 | 2021/08/15 | 2021/09/24 | 2021/08/18 | 2021/09/28 | 2022/03/11 | 2021/12/16
BEEPAF-165405-RFB-07-W-21-FBIH / Works on reconstruction of 2 objects in Canton Tuzla | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Works (without prequalification) SPD | Signed | Cleared | [9 empty] | 2021/06/15 | 2021/06/18 | 2021/06/20 | 2021/06/18 |  |  |  | 2021/07/20 | 2021/07/16 | 2021/07/30 | 2021/07/26 | 2021/08/13 | 2021/08/30 | 2021/08/16 | 2021/09/02 | 2022/03/11 | 2021/12/14
BEEPAF-165405-RFB-09-W-21-FBIH / Works on reconstruction of 5 objects in ZE-DO canton | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Works (without prequalification) SPD | Signed | Cleared | [9 empty] | 2021/06/16 | 2021/06/23 | 2021/06/21 | 2021/06/23 |  |  |  | 2021/07/21 | 2021/07/21 | 2021/07/31 | 2021/08/25 | 2021/08/14 | 2021/09/16 | 2021/08/17 | 2021/09/17 | 2022/01/27 | 2021/12/15
B EEP-PI 4 3580-NCB-30-W15 - FBIH / Works for implementation of energy efficiency measures for university clinical center Mostar Lot 1 and university clinical center Tuzla surgery clinic Gradina Lot 2 | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Works | Open - National | N | Single Stage One Envelope |  |  |  | Signed | Cleared | [19 empty] | 2015/09/29 |  |  |  | 2015/12/18
BEEPAF-P165405-RFB-03-G-22-FBIH / Equipment for measuring the heat energy consumption/temperatures and Equipment for remote reading of meters in a wired M-bus system | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Open - National | N | Single Stage One Envelope |  |  | Request for Bids SPD (Goods) - 1 envelope process | Pending Implementation | Cleared | [9 empty] | 2022/11/28 |  | 2022/11/30 |  |  |  |  | 2022/12/28 |  | 2022/12/29 |  | 2023/01/12 |  | 2023/01/15 |  |  | 2023/05/15
BEEPAF-165405-RFB-11-W-21-FBIH / Works on reconstruction of 5 objects in ZE-DO canton | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Works (without prequalification) SPD | Signed | Cleared | [9 empty] | 2021/06/18 | 2021/06/23 | 2021/06/23 | 2021/06/23 |  |  |  | 2021/07/23 | 2021/07/21 | 2021/08/02 | 2021/08/25 | 2021/08/16 | 2021/09/16 | 2021/08/19 | 2021/09/17 | 2022/01/27 | 2021/12/17
BEEPAF-P165405-RFB-02-W-21-FBIH / Works on reconstruction of 13 objects in 2021 | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  |  | Signed | Cleared | [9 empty] | 2021/04/01 | 2021/05/28 | 2021/04/11 | 2021/05/28 |  |  |  | 2021/05/09 | 2021/06/28 | 2021/05/23 | 2021/06/30 | 2021/06/01 | 2021/07/22 | 2021/06/17 | 2021/07/26 | 2022/03/10 | 2021/10/15
BEEPAF-P165405-RFB-06-W-22-FBIH / Works on reconstruction of 10 objects in 2022. | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  |  | Under Implementation | Cleared | [9 empty] | 2022/04/01 | 2022/07/04 | 2022/04/11 |  |  |  |  | 2022/05/09 | 2022/08/02 | 2022/05/23 | 2022/08/25 | 2022/06/01 | 2022/10/24 | 2022/06/17 |  |  | 2022/10/15
BEEPAF-P165405-RFB-01-G-21-FBIH / "Purchasing and Installation (Performance Monitoring System for measuring the temperature and humidity) (38 buildings) " | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Open - National | N | Single Stage One Envelope |  |  |  | Signed | Cleared | [9 empty] | 2021/02/03 | 2021/02/08 | 2021/02/05 |  |  |  |  | 2021/02/26 | 2021/03/02 | 2021/03/03 | 2021/03/11 | 2021/03/04 | 2021/03/23 | 2021/03/07 | 2021/03/23 | 2021/05/07 | 2021/04/21
BEEPAF-P165405-NCB-02-G-21-FBIH / "Purchasing and Instalation (Performance Monitoring System for measuring the temperature and humidity) (25 buildings) - 2020. buldings (allocated)" | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Open - National | N | Single Stage One Envelope |  |  |  | Canceled | Cleared | [9 empty] | 2021/01/15 |  | 2021/01/17 |  |  |  |  | 2021/02/07 |  | 2021/02/12 |  | 2021/02/13 |  | 2021/02/16 |  |  | 2021/03/08
BEEPAF-P165405-RFB-02-G-22-FBIH / "Purchasing and Installation (Performance Monitoring System for measuring the temperature and humidity) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Open - National | N | Single Stage One Envelope |  |  |  | Pending Implementation | Cleared | [9 empty] | 2022/01/15 |  | 2022/01/17 |  |  |  |  | 2022/02/07 |  | 2022/02/12 |  | 2022/02/13 |  | 2022/02/16 |  |  | 2022/03/18
-P143580-BA-BEEP-5393BA-NCB-W-15-5-RS / RETROFITTING OF JZU BOLNICA ZVORNIK | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Works | Open - National | N | Single Stage One Envelope |  |  |  | Under Implementation | Cleared | [19 empty] | 2016/04/20
BEEPAF-P165405-RFB-03-G-23-FBIH / "Purchasing and Installation (Performance Monitoring System for measuring the temperature and humidity) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Open - National | N | Single Stage One Envelope |  |  |  | Pending Implementation | Cleared | [9 empty] | 2023/01/15 |  | 2023/01/17 |  |  |  |  | 2023/02/07 |  | 2023/02/12 |  | 2023/02/13 |  | 2023/02/16 |  |  | 2023/03/18
BEEPAF-P165405-RFB-04-W-23-FBIH / Works on reconstruction of (1+5) objects in 2023 | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  |  | Pending Implementation | Cleared | [9 empty] | 2023/04/01 |  | 2023/04/11 |  |  |  |  | 2023/05/09 |  | 2023/05/23 |  | 2023/06/01 |  | 2023/06/17 |  |  | 2023/10/15
BEEPAF-165405-RFB-08-W-21-FBIH / Works on reconstruction of 5 objects in ZE-DO canton | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Works (without prequalification) SPD | Signed | Cleared | [9 empty] | 2021/06/15 | 2021/06/23 | 2021/06/20 | 2021/06/23 |  |  |  | 2021/07/20 | 2021/07/21 | 2021/07/30 | 2021/09/08 | 2021/08/13 | 2021/09/24 | 2021/08/16 | 2021/09/28 | 2022/04/25 | 2021/12/14
BEEPAF-P165405-RFB-13-W-22-FBIH / Works on reconstruction on one object in Canton Sarajevo | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Works (without prequalification) SPD | Signed | Cleared | [9 empty] | 2022/07/16 | 2022/07/27 | 2022/07/21 |  |  |  |  | 2022/08/18 | 2022/08/25 | 2022/09/01 | 2022/08/25 | 2022/09/15 | 2022/10/07 | 2022/09/20 |  |  | 2023/01/18
P143580-BA-BEEP-5393BA-NCB-W-14-4-RS / Retrofitting of University Hospital Foca | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Works | Open - National | N | Single Stage One Envelope |  |  |  | Under Implementation | Cleared | [19 empty] | 2016/04/20
BEEPAF-P165405-RFB-05-W-21-FBIH / Works on reconstruction of 12 objects in 2021. | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  |  | Signed | Cleared | [9 empty] | 2021/04/01 | 2021/05/31 | 2021/04/11 | 2021/05/31 |  |  |  | 2021/05/09 | 2021/06/30 | 2021/05/23 | 2021/07/01 | 2021/06/01 | 2021/07/22 | 2021/06/17 | 2021/07/26 | 2022/03/10 | 2021/10/15
BEEPAF-P165405-NCB-01-G-20-FBIH / "Purchasing and Instalation (Performance Monitoring System for measuring the temperature and humidity) (20 buildings) - 2020. buldings (allocated)" | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Open - National | N | Single Stage One Envelope |  |  |  | Canceled | Cleared | [9 empty] | 2020/07/15 |  | 2020/07/17 |  |  |  |  | 2020/08/07 |  | 2020/08/12 |  | 2020/08/13 |  | 2020/08/16 |  |  | 2020/09/05
BEEPAF-P165405-RFB-01-W-20-FBIH / Works on reconstruction of 3 objects in KS | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Works (without prequalification) SPD | Canceled | Cleared | [9 empty] | 2020/09/01 | 2021/06/17 | 2020/09/11 | 2021/06/17 |  |  |  | 2020/10/09 |  | 2020/10/23 |  | 2020/11/01 |  | 2020/11/17 |  |  | 2021/03/17
BEEPAF-P165405-RFB-03-W-22-FBIH / Works on reconstruction of 10 objects in 2022 | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Works | Open - National | N | Single Stage One Envelope |  |  |  | Signed | Cleared | [9 empty] | 2022/04/01 | 2022/04/28 | 2022/04/11 |  |  |  |  | 2022/05/09 | 2022/05/30 | 2022/05/23 | 2022/06/17 | 2022/06/01 | 2022/10/07 | 2022/06/17 |  |  | 2022/10/15
BEEPAF-P165405-NCB-03-G-22-FBIH / "Purchasing and Instalation (Performance Monitoring System for measuring the temperature and humidity) (20 buildings) - 2022. buldings (allocated)" | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Open - National | N | Single Stage One Envelope |  |  |  | Canceled | Cleared | [9 empty] | 2022/01/15 |  | 2022/01/17 |  |  |  |  | 2022/02/07 |  | 2022/02/12 |  | 2022/02/13 |  | 2022/02/16 |  |  | 2022/03/08
BEEPAF-P165405-RFB-01-NCS-21-FBIH / ENERGY EFFICIENCY SERVICES for implementation of energy efficiency measures, including engineering design, construction works, measurement and verification of savings and first year operations and maintenance services | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Non-consulting Services | Open - National | N | Single Stage One Envelope |  |  | Request for Bids - Non-consulting Services SPD | Pending Implementation | Cleared | [9 empty] | 2021/06/30 |  | 2021/07/05 |  |  |  |  | 2021/08/04 |  | 2021/08/19 |  | 2021/09/02 |  | 2021/09/07 |  |  | 2023/03/11

## RFQ
Request for Quotations
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | High SEA/SH Risk | Procurement Document Type | Process Status | Activity Status | Draft Request for Quotations |  | Specific Procurement Notice |  | Invitation to Supplier / Contractor |  | Amendments to Request for Quotations | Receive Quotations |  | Comparison of Quotations |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[11 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BEEPAF-P165405-RFQ-07-G-20-FBIH / Purchasing of Furniture required PIU | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Limited |  |  | Completed | Cleared | 2020/05/10 | 2020/05/20 | [5 empty] | 2020/06/03 | 2020/06/10 | 2020/06/04 | 2020/10/09 | 2020/06/07 | 2020/10/09 | 2020/06/07 | 2020/10/26 |  | 2020/06/27 | 2020/11/30
BEEPAF-P165405-RFQ-12-G-22-FBIH / Equipment for measuring the heat energy consumption and internal and external temperatures and Equipment for remote reading of meters in a wired M-bus system | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Open - National |  | Other (with field for explanation) | Signed | Cleared | 2022/10/10 | 2022/10/19 | 2022/10/13 |  | 2022/10/14 | 2022/11/04 |  | 2022/10/28 | 2022/11/04 | 2022/11/04 | 2022/11/09 | 2022/11/07 | 2022/11/23 | 2022/11/09 |  |  | 2023/03/09
BEEPAF-P165405-RFQ-10-G-21-FBIH / Procurement of equipment for video conference | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Limited |  | Other (with field for explanation) | Signed | Cleared | 2021/06/25 | 2021/09/06 | [5 empty] | 2021/07/10 | 2021/10/24 | 2021/07/17 | 2021/09/29 | 2021/07/20 | 2021/10/05 | 2021/07/23 | 2021/10/15 |  | 2021/09/21
BEEPAF-P165405-RFQ-11-G-22-FBIH / Equipment for measuring the heat energy consumption and temperature/humidity and Equipment for remote reading of meters in a wired M-bus system | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Limited |  | Other (with field for explanation) | Canceled | Cleared | 2022/07/20 | 2022/08/30 | [5 empty] | 2022/08/04 | 2022/09/15 | 2022/08/11 |  | 2022/08/14 |  | 2022/08/17 |  |  | 2022/10/16
BEEPAF-P165405-RFQ-06-G-20-FBIH / Purchasing and Instalation of IT Equipment required PIU | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Limited |  |  | Signed | Cleared | 2020/05/15 | 2020/12/16 | [5 empty] | 2020/06/03 | 2021/01/18 | 2020/06/04 | 2021/01/29 | 2020/06/07 | 2021/02/11 | 2020/06/07 | 2021/02/15 | 2021/03/17 | 2020/06/27
BEEPAF-P165405-RFQ-08-G-20-FBIH / Contract Management Software | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Limited |  |  | Pending Implementation | Cleared | 2020/09/15 | [6 empty] | 2020/10/04 |  | 2020/10/11 |  | 2020/10/14 |  | 2020/10/16 |  |  | 2020/12/15
BEEPAF--P165405-RFQ-09-G-21-FBIH / Purchasing and Installation (Performance Monitoring System for measuring the temperature and humidity | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Limited |  | Other (with field for explanation) | Signed | Cleared | 2021/06/28 | 2021/09/21 | [5 empty] | 2021/07/13 | 2021/10/07 | 2021/07/20 | 2021/10/15 | 2021/07/23 | 2021/10/21 | 2021/07/26 | 2021/10/26 | 2022/01/31 | 2021/08/25
P143580-BA-BEEP-5393BA-SH-G-14-13-RS / Supply of metering equipment | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Goods | Open - International |  |  | Signed | Cleared | [10 empty] | 2016/03/22 |  |  |  | 2016/03/22
BEEPAF-P165405-RFQ-04-G-23-FBIH / "Purchasing and Instalation (Performance Monitoring System for measuring the temperature and humidity) (6 buildings) - 20232. buldings (allocated)" | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Limited |  |  | Pending Implementation | Cleared | 2023/01/15 | [6 empty] | 2023/02/03 |  | 2023/02/04 |  | 2023/02/07 |  | 2023/02/07 |  |  | 2023/02/27
BEEPAF-P165405-RFQ-05-G-20-FBIH / Purchasing and Instalation of Equipment required for Energy efficiency information system update (EE Revolving fund) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Goods | Limited |  |  | Pending Implementation | Cleared | 2020/09/01 | [6 empty] | 2020/09/20 |  | 2020/09/21 |  | 2020/09/24 |  | 2020/09/24 |  |  | 2020/10/14

## QBS
Quality Based Selection (QBS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Request for Proposals as Issued |  | Amendments to Request for Proposals |  | Opening of Technical Proposals / Minutes |  | Evaluation of Technical Proposals |  | Combined Evaluation Report and Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BA-BEEP-5393BA-QBS-CS-14-16-RS / Preparation of technical design and works supervision for retrofitting of public buildings | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open - International | Signed | Cleared | [17 empty] | 2016/05/18 |  |  |  | 2016/05/19

## CQS
Consultant Qualification
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Short List and Draft Request for Proposals |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BEEP-P143580-CQ-02-CS-15-FBIH-II / Performing works supervision, technical monitoring and evaluation and energy labelling | No | IDA-53930,IDA-55380 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open - International | Signed | Cleared | [9 empty] | 2015/07/08 |  |  |  | 2015/12/17
BEEPAF-P165405-CQ-24-CS-20-FBIH / Other training and capacity buildings (local Governments, local energy service providers, etc.) | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Canceled | Cleared | 2020/11/01 |  | 2020/11/15 |  | 2020/11/22 |  | 2020/11/23 |  | 2020/12/07 |  | 2020/12/07 |  | 2020/12/09 |  |  | 2024/10/09
BEEPAF-P165405-CQ-36-CS-21-FBIH / TA to the Revolving fund | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Signed | Cleared | 2021/11/22 | 2021/12/08 | 2021/12/06 |  | 2021/12/16 | 2022/03/09 | 2021/12/19 | 2022/03/15 | 2022/01/08 | 2022/04/01 | 2022/01/11 | 2022/04/12 | 2022/01/16 | 2022/04/15 |  | 2022/07/15
BEEPAF-P165405-CQ-14-CS-22-FBIH / Energy certificates | No | IDA-55380 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2022/01/10 |  | 2022/01/29 |  | 2022/02/05 |  | 2022/02/06 |  | 2022/02/20 |  | 2022/02/20 |  | 2022/02/22 |  |  | 2022/05/23
BA-BEEP-CQ-08-CS-14-5393BA-RS- / performing detailed energy audits, monitoring and evaluation, technical design, supervision and technical documentation for energy labels for retrofitted public buildings | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open - International | Signed | Cleared | [9 empty] | 2015/07/10 |  |  |  | 2015/07/13
BEEP-P143580-CQ-02-CS-15-FBIH-I / Performing Works Supervision, Technical Monitoring and Evaluation and Energy Labelling | No | IDA-53930,IDA-55380 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open - International | Signed | Cleared | [9 empty] | 2015/07/08 |  |  |  | 2015/12/17
BEEPAF-P165405-CQ-12-CS-20-FBIH / Energy certificates | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Under Implementation | Cleared | 2020/07/10 | 2020/05/15 | 2020/07/29 |  | 2020/08/05 |  | 2020/08/06 |  | 2020/08/20 |  | 2020/08/20 |  | 2020/08/22 |  |  | 2020/11/20
BEEPAF-P165405-CQ-28-CS-20-FBIH / Communication and Promotion Public Campaigns | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Signed | Cleared | 2020/05/10 | 2020/05/07 | 2020/05/29 |  | 2020/06/05 | 2020/07/28 | 2020/06/06 | 2020/08/03 | 2020/06/20 | 2020/10/16 | 2020/06/20 | 2020/10/20 | 2020/06/22 | 2020/10/16 |  | 2024/04/22
BEEPAF-P165405-CQ-09-CS-23-FBIH / Design and tecnical supervision (1+5=6 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2023/01/10 |  | 2023/01/29 |  | 2023/02/05 |  | 2023/02/06 |  | 2023/02/20 |  | 2023/02/20 |  | 2023/02/22 |  |  | 2023/08/21
BEEPAF-P165405-CQ-34-CS-21-FBIH / Stocktaking of all public buildings, development of digital map-based platform, overview of the public buildings that need the EE renovation | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Signed | Cleared | 2021/11/22 | 2021/12/13 | 2021/12/06 |  | 2021/12/16 | 2022/02/23 | 2021/12/19 | 2022/03/07 | 2022/01/08 | 2022/03/30 | 2022/01/11 | 2022/04/12 | 2022/01/16 | 2022/04/21 | 2022/07/26 | 2022/07/15
BEEPAF-P165405-CQ-02-CS-21-FBIH / Detailed energy audits - 52 buildings | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2021/01/10 | 2021/08/26 | 2021/01/29 |  | 2021/02/05 | 2021/09/20 | 2021/02/06 | 2021/09/22 | 2021/02/20 | 2021/10/06 | 2021/02/20 | 2021/10/28 | 2021/02/22 | 2021/11/05 | 2022/02/28 | 2021/05/23
BEEPAF-P165405-CQ-05-CS-21-FBIH / Design and technical supervision (11 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2021/01/10 | 2021/07/29 | 2021/01/29 | 2021/07/30 | 2021/02/05 | 2021/09/08 | 2021/02/06 | 2021/09/16 | 2021/02/20 | 2021/10/07 | 2021/02/20 | 2021/11/08 | 2021/02/22 | 2021/11/21 | 2022/02/23 | 2021/08/21
BEEPAF-P165405-CQ-03-CS-20-FBIH / Design and technical supervision (10 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2020/07/10 | 2020/12/17 | 2020/07/29 |  | 2020/08/05 | 2021/01/26 | 2020/08/06 | 2021/01/26 | 2020/08/20 | 2021/02/19 | 2020/08/20 | 2021/02/25 | 2020/08/22 | 2021/03/03 | 2022/05/27 | 2021/02/18
BEEPAF-P165405-CQ-46-CS-23-FBIH / Provision of consulting services related to the preparation and organization of the Second International Conference on Energy Efficiency in Public Buildings | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Under Review | Cleared | 2023/05/10 | 2023/05/10 | 2023/05/24 |  | 2023/05/31 |  | 2023/06/10 |  | 2023/06/13 |  | 2023/07/13 |  | 2023/07/16 |  |  | 2023/07/31
BEEPAF-P165405-CQ-45-CS-23-FBIH / Provision of consulting services related to the development of Study of alternative heating systems in buildings in FBiH | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Under Review | Cleared | 2023/05/10 | 2023/05/10 | 2023/05/24 |  | 2023/05/31 |  | 2023/06/10 |  | 2023/06/13 |  | 2023/06/16 |  | 2023/06/19 |  |  | 2024/01/15
BEEPAF-P165405-CQ-37-CS-22-FBIH / Design and works supervision (14 objects) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Under Implementation | Cleared | 2022/11/22 | 2022/11/22 | 2022/12/06 |  | 2022/12/13 | 2023/01/31 | 2022/12/16 | 2023/02/02 | 2022/12/23 | 2023/02/20 | 2022/12/26 | 2023/02/23 | 2022/12/28 |  |  | 2023/03/28
BEEPAF-P165405-CQ-40-CS-23-FBIH / Energy certification (up to 30 objects) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2023/06/20 |  | 2023/07/04 |  | 2023/07/11 |  | 2023/07/14 |  | 2023/07/21 |  | 2023/07/24 |  | 2023/07/26 |  |  | 2023/10/24
BEEPAF-P165405-CQ-04-CS-20-FBIH / Audit of design (11+9=20 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2020/07/10 | 2020/05/08 | 2020/07/29 |  | 2020/08/05 | 2021/01/19 | 2020/08/06 | 2021/01/28 | 2020/08/20 | 2021/02/16 | 2020/08/20 | 2021/02/25 | 2020/08/22 | 2021/03/03 | 2022/02/24 | 2020/10/21
BEEPAF-P165405-CQ-43-CS-23-FBIH / Provision of consulting services related to drafting the amendments and additions to the Regulation on conducting energy audits and issuing energy certificates and to the Rulebook on minimum requirements for the energy characteristics of buildings | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Under Implementation | Cleared | 2023/05/10 | 2023/05/10 | 2023/05/24 |  | 2023/05/31 |  | 2023/06/01 |  | 2023/06/17 |  | 2023/06/20 |  | 2023/07/07 |  |  | 2024/01/03
BA-BEEP-CQ-22-CS-14-5393BA-RS / communication activities services | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open - International | Signed | Cleared | [9 empty] | 2015/06/04 |  |  |  | 2015/06/11
BEEPAF-P165405-CQ-23-CS-23-FBIH / Training for beneficiaries and energy managements | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2023/01/10 |  | 2023/01/29 |  | 2023/02/05 |  | 2023/02/06 |  | 2023/02/20 |  | 2023/02/20 |  | 2023/02/22 |  |  | 2026/12/23
BEEPAF-P165405-CQ-07-CS-22-FBIH / Design and technical supervision (10 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2022/01/10 |  | 2022/01/29 |  | 2022/02/05 |  | 2022/02/06 |  | 2022/02/20 |  | 2022/02/20 |  | 2022/02/22 |  |  | 2022/08/21
BEEPAF-P165405-CQ-42-CS-23-FBIH / Provision of consulting services related to the development of the Second Operational Plan for improving energy efficiency in FBiH institutions | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Under Review | Cleared | 2023/05/10 | 2023/05/10 | 2023/05/24 |  | 2023/05/31 |  | 2023/06/10 |  | 2023/06/13 |  | 2023/07/13 |  | 2023/07/16 |  |  | 2024/02/11
BEEPAF-P165405-CQ-27-CS-20-FBIH / Energy efficiency information system updates (e.g. EE Revolving fund) | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Under Implementation | Cleared | 2021/11/22 | 2021/12/08 | 2021/12/06 |  | 2021/12/16 |  | 2021/12/19 |  | 2022/01/08 |  | 2022/01/11 |  | 2022/01/16 |  |  | 2022/07/15
BEEPAF-P165405-CQ-21-CS-21-FBIH / Training for beneficiaries and energy managements | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2021/10/29 |  | 2021/11/12 |  | 2021/11/19 |  | 2021/11/22 |  | 2021/12/06 |  | 2021/12/09 |  | 2021/12/12 |  |  | 2022/02/10
BEEPAF-P165405-CQ-10-CS-23-FBIH / Audit of design (1+5=6 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2023/01/10 |  | 2023/01/29 |  | 2023/02/05 |  | 2023/02/06 |  | 2023/02/20 |  | 2023/02/20 |  | 2023/02/22 |  |  | 2023/04/23
BEEPP143580CQ-05-CS-15-FBIH I and II / Design and technical monitoring ( Lump Sum ) and Supervision ( Time Based) | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open - International | Signed | Cleared | [9 empty] | 2016/02/12 |  |  |  | 2016/02/15
BA-BEEP-CQ-08-CS-14-5393BA-RS / Performing detailed energy audits, monitoring and evaluation, technical design, supervision and technical documentation for energy labels for retrofitted public buildings | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open - International | Signed | Cleared | [9 empty] | 2016/06/15 |  |  |  | 2015/07/13
BEEPAF-P165405-CQ-15-CS-23-FBIH / Energy certificates | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2023/01/10 |  | 2023/01/29 |  | 2023/02/05 |  | 2023/02/06 |  | 2023/02/20 |  | 2023/02/20 |  | 2023/02/22 |  |  | 2023/05/23
BEEPAF-P16405-CQ-39-CS-22-FBIH / Audit of design (25 objects) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2022/11/22 | 2022/11/22 | 2022/12/06 |  | 2022/12/13 | 2023/01/31 | 2022/12/16 | 2023/02/02 | 2022/12/23 | 2023/02/20 | 2022/12/26 | 2023/02/23 | 2022/12/28 |  |  | 2023/03/28
BEEPAF-P165405-CQ-25-CS-20-FBIH / Capacity building Ministry and PIU | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Signed | Cleared | 2021/11/22 | 2021/11/26 | 2021/12/06 |  | 2021/12/16 | 2022/03/08 | 2021/12/19 | 2022/03/22 | 2022/01/08 | 2022/03/08 | 2022/01/11 | 2022/04/14 | 2022/01/16 | 2022/04/15 |  | 2023/04/11
BEEPAF-P165405-CQ-35-CS-21-FBIH / Assessment of the energy use and energy savings through EE investment in eligible public buildings | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Signed | Cleared | 2021/11/22 | 2021/12/13 | 2021/12/06 |  | 2021/12/16 | 2022/02/23 | 2021/12/19 | 2022/03/07 | 2022/01/08 | 2022/03/30 | 2022/01/11 | 2022/04/12 | 2022/01/16 | 2022/04/21 | 2022/07/28 | 2022/07/15
BEEPAF-P165405-CQ-33-CS-21-FBIH / Design and technical supervision (7 objects) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2021/06/18 | 2021/07/30 | 2021/07/02 |  | 2021/07/09 | 2021/09/20 | 2021/07/12 | 2021/09/22 | 2021/07/27 | 2021/10/06 | 2021/07/30 | 2021/11/08 | 2021/08/02 | 2021/11/21 | 2022/07/25 | 2021/10/01
BEEPAF-P165405-CQ-29-CS-20-FBIH / Design and technical supervision (10 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2020/07/10 | 2020/05/08 | 2020/07/29 |  | 2020/08/05 | 2021/01/26 | 2020/08/06 | 2021/01/26 | 2020/08/20 | 2021/02/10 | 2020/08/20 | 2021/02/25 | 2020/08/22 | 2021/03/03 | 2022/03/30 | 2021/02/18
BEEPAF-P165405-CQ-20-CS-20-FBIH / Training for beneficiaries and energy managements | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Signed | Cleared | 2020/07/10 | 2021/12/08 | 2020/07/29 |  | 2020/08/05 | 2022/02/03 | 2020/08/06 | 2022/02/11 | 2020/08/20 | 2022/03/11 | 2020/08/20 | 2022/03/15 | 2020/08/22 | 2022/03/21 |  | 2024/06/22
BEEPAF-P165405-CQ-22-CS-22-FBIH / Training for beneficiaries and energy managements | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2022/01/10 |  | 2022/01/29 |  | 2022/02/05 |  | 2022/02/06 |  | 2022/02/20 |  | 2022/02/20 |  | 2022/02/22 |  |  | 2025/12/23
BEEPAF-P165405-CQ-30-CS-21-FBIH / Design and technical supervision (10 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2021/01/10 | 2020/12/17 | 2021/01/29 |  | 2021/02/05 | 2021/01/26 | 2021/02/06 | 2021/01/26 | 2021/02/20 | 2021/02/10 | 2021/02/20 | 2021/02/25 | 2021/02/22 | 2021/03/03 | 2022/03/30 | 2021/08/21
BEEPAF-P165405-CQ-32-CS-22-FBIH / Design and technical supervision (10 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2022/01/10 |  | 2022/01/29 |  | 2022/02/05 |  | 2022/02/06 |  | 2022/02/20 |  | 2022/02/20 |  | 2022/02/22 |  |  | 2022/08/21
BEEPAF-P165405-CQ-44-CS-23-FBIH / Provision of consultanting services related to the development of the Guidelines for energy renovation of buildings, which have the status of a national monument or are located within the scope of the buffer zone of the national monument of the ambient en | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2023/05/10 |  | 2023/05/24 |  | 2023/05/31 |  | 2023/06/10 |  | 2023/06/13 |  | 2023/06/16 |  | 2023/06/19 |  |  | 2023/12/16
BEEPAF-P165405-CQ-41-CS-23-FBIH / Energy training (up to 30 objects) | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2023/06/20 |  | 2023/07/04 |  | 2023/07/11 |  | 2023/07/14 |  | 2023/07/21 |  | 2023/07/24 |  | 2023/07/26 |  |  | 2023/10/24
BEEPAF-P165405-CQ-38-CS-22-FBIH / Design and works supervision (11 objects) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2022/11/22 | 2022/11/22 | 2022/12/06 |  | 2022/12/13 | 2023/01/31 | 2022/12/16 | 2023/02/02 | 2022/12/23 | 2023/02/20 | 2022/12/26 | 2023/02/23 | 2022/12/28 |  |  | 2023/03/28
BEEPAF-P165405-CQ-26-CS-21-FBIH / Targeted women training | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Open - National | Signed | Cleared | 2021/11/22 | 2021/12/08 | 2021/12/06 |  | 2021/12/16 | 2022/02/03 | 2021/12/19 | 2022/02/11 | 2021/12/21 | 2022/03/15 | 2021/12/24 | 2022/03/14 | 2021/12/29 | 2022/03/27 | 2022/08/01 | 2022/06/27
BEEPAF-P165405-CQ-31-CS-21-FBIH / Design and technical supervision (5 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2021/01/10 | 2020/12/17 | 2021/01/29 |  | 2021/02/05 | 2021/01/15 | 2021/02/06 | 2021/01/26 | 2021/02/20 | 2021/02/19 | 2021/02/20 | 2021/02/25 | 2021/02/22 | 2021/03/03 | 2022/03/30 | 2021/08/21
BEEP-P143580-CQ-05-CS-15-FBIH I and II / Consulting services to perform design, technical monitoring services - (before and after ) Works Supervision | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open - International | Signed | Cleared | [9 empty] | 2016/02/12 |  |  |  | 2016/02/15
BEEPAF-P165405-CQ-01-CS-20-FBIH / Detailed energy audits - 50 buildings | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2020/07/10 | 2020/05/07 | 2020/07/29 |  | 2020/08/05 | 2020/11/11 | 2020/08/06 | 2020/11/11 | 2020/08/20 | 2020/12/22 | 2020/08/20 | 2021/01/07 | 2020/08/22 | 2021/01/11 |  | 2020/11/20
BEEPAF-P165405-CQ-11-CS-20-FBIH / Social monitoring and evaluation (up to 18 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2020/06/10 | 2020/05/12 | 2020/06/29 |  | 2020/07/06 | 2020/10/08 | 2020/07/07 | 2020/10/09 | 2020/07/20 | 2020/12/09 | 2020/07/20 | 2020/12/09 | 2020/07/23 | 2020/12/11 | 2021/09/10 | 2020/10/21
BEEPAF-P165405-CQ-08-CS-22-FBIH / Audit of design (14+6=20 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Pending Implementation | Cleared | 2022/01/10 |  | 2022/01/29 |  | 2022/02/05 |  | 2022/02/06 |  | 2022/03/08 |  | 2022/03/08 |  | 2022/03/10 |  |  | 2022/05/09
BEEPAF-P165405-CQ-06-CS-21-FBIH / Audit of design (7 buildings) | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2021/01/10 | 2021/07/30 | 2021/01/29 |  | 2021/02/05 | 2021/11/04 | 2021/02/06 | 2021/11/11 | 2021/02/20 | 2021/12/01 | 2021/02/20 | 2021/12/02 | 2021/02/22 | 2021/12/08 | 2022/03/31 | 2021/04/23
BEEPAF-P165405-CQ-13-CS-21-FBIH / Energy certificates | No | IBRD-89060 | Energy Efficiency Investments in Public Facilities | Post | Consultant Services | Open - National | Signed | Cleared | 2021/10/29 | 2021/12/13 | 2021/11/12 |  | 2021/11/19 | 2022/02/02 | 2021/11/22 | 2022/02/11 | 2021/12/06 | 2022/04/10 | 2021/12/09 | 2022/04/12 | 2021/12/12 | 2022/04/15 | 2022/07/27 | 2022/02/10

## CDS
Consultant Direct Selection (CDS)
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Process Status | Activity Status | Terms of Reference |  | Justification for Direct Selection |  | Invitation to Identified/Selected Consultant |  | Amendments to Terms of Reference |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BEEP-P I 43580-SSS-28-CS-1S-FBIH / Consulting services for Financial software procurement | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Direct | Signed | Cleared | [9 empty] | 2015/11/02 |  |  |  | 2015/12/16

## INDV
Individual Consultant Selection
Activity Reference No. / Description: | In-Process | Loan / Credit No. | Component | Review Type | Category | Market Approach | Process Status | Activity Status | Terms of Reference |  | Expression of Interest |  | Evaluation of Expression of Interest and Short List of Consultants |  | Justification for Direct Selection |  | Invitation to Identified / Selected Consultant |  | Draft Negotiated Contract |  | Notification of Intention of Award |  | Signed Contract |  | Contract Amendments | Contract Completion |  | Contract Termination
[9 empty] | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Actual | Planned | Actual | Actual
BEEP-P143580-IC-06-CS-14-FBIH / FINANCIAL SPECIALIST | No | IDA-55380 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Under Implementation | Cleared | [11 empty] | 2017/05/09
BEEPAF-P165405-IC-19-CS-20-FBIH / Development / Technical Assistance for EE Revolving fund / Technical Expert | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Limited | Signed | Cleared | 2020/05/10 | 2020/06/09 | [6 empty] | 2020/05/15 | 2020/09/10 | 2020/06/20 | 2020/10/22 | 2020/06/20 | 2020/10/18 | 2020/06/22 | 2020/10/22 | 2021/05/17 | 2024/04/22
BEEPAF-P165405-IC-20-CS-23-FBIH / Provision of consulting services related to the strengthening of institutional framework and the energy efficiency management system capacity development through design of the feasibility study for establishment of the Energy Efficiency Agency in Federat | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Limited | Pending Implementation | Cleared | 2023/05/16 | [7 empty] | 2023/05/21 |  | 2023/05/31 |  | 2023/06/03 |  | 2023/06/06 |  |  | 2023/12/03
BEEP-P143580-IC-25-CS-14-FBIH / Procurement Specialist | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Terminated | Cleared | [11 empty] | 2015/11/28 |  |  |  | 2015/12/16
BEEP-P143580-IC-005-FBIH / Technical Expert I in the Project Implementation Unit of the Federation Ministry of Physical Planning | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Terminated | Cleared | [11 empty] | 2015/11/28 |  |  |  | 2015/12/16
BEEPAF-P165405-IC-02-CS-20-FBIH / Procurement Specialist | No | IBRD-89060 | Project Management | Prior | Consultant Services | Direct | Signed | Cleared | 2020/05/10 | 2020/06/04 |  |  |  |  | 2020/05/15 | 2020/06/04 | 2020/05/23 | 2020/06/04 | 2020/06/06 | 2020/06/08 | 2020/06/06 | 2020/06/16 | 2020/06/08 | 2020/06/09 |  | 2024/05/01
BEEP-P143580-IC-26-CS-14-FBH / Technical Expert | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Terminated | Cleared | [11 empty] | 2015/11/28 |  |  |  | 2015/12/16
BEEP-P143580-IC-27-CS-14-FBH / For a Administrative Assistant in the Project Implementation Unit of the Federation Ministry of Physical Planning | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Canceled | Cleared | [11 empty] | 2015/11/28
BEEP-P143580-IC-003-FBIH / For a Administrative Assistant in the Project Implementation Unit of the Federation Ministry of Physical Planning | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Terminated | Cleared | [11 empty] | 2015/12/22 |  |  |  | 2015/12/16
BEEPAF-P165405-IC-01-CS-20-FBIH / Project Leader | No | IBRD-89060 | Project Management | Prior | Consultant Services | Direct | Signed | Cleared | 2020/05/10 | 2020/06/04 |  |  |  |  | 2020/05/15 | 2020/06/04 | 2020/05/23 | 2020/06/04 | 2020/06/06 | 2020/06/08 | 2020/06/06 | 2020/06/16 | 2020/06/08 | 2020/06/09 |  | 2024/05/01
BEEPAF-P165405-IC-03-CS-20-FBIH / Financial Management Specialist | No | IBRD-89060 | Project Management | Prior | Consultant Services | Direct | Signed | Cleared | 2020/05/10 | 2020/06/04 |  |  |  |  | 2020/05/15 | 2020/06/04 | 2020/05/23 | 2020/06/04 | 2020/06/06 | 2020/06/08 | 2020/06/06 | 2020/06/16 | 2020/06/08 | 2020/06/09 |  | 2024/05/01
. P143580-BA-BEEP-5393BA-IC-CS-15-26-RS / Procurement Manager | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Signed | Cleared | [11 empty] | 2017/11/06 |  |  |  | 2017/11/01
BEEPAF-P165405-IC-06-CS-20-FBIH / Technical Expert III | No | IBRD-89060 | Project Management | Prior | Consultant Services | Direct | Signed | Cleared | 2020/05/10 | 2020/06/04 |  |  |  |  | 2020/05/15 | 2020/06/04 | 2020/05/23 | 2020/06/04 | 2020/06/06 | 2020/06/08 | 2020/06/06 | 2020/06/16 | 2020/06/08 | 2020/06/09 |  | 2024/05/01
BEEPAF-P165405-IC-17-CS-20-FBIH / Development / Technical Assistance for EE Revolving fund /Financial Expert | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Limited | Signed | Cleared | 2020/05/10 | 2020/06/09 | [6 empty] | 2020/05/15 | 2020/09/09 | 2020/06/20 | 2020/10/22 | 2020/06/20 | 2020/10/18 | 2020/06/22 | 2020/10/22 |  | 2024/04/22
BEEPAF-P165405-IC-08-CS-20-FBIH / Administrative Assistant | No | IBRD-89060 | Project Management | Post | Consultant Services | Limited | Signed | Cleared | 2020/05/01 | 2020/02/18 | [6 empty] | 2020/05/01 | 2020/05/08 | 2020/06/06 | 2020/05/18 | 2020/06/06 | 2020/05/18 | 2020/06/08 | 2020/05/18 |  | 2024/05/01
BEEPAF-P165405-IC-18-CS-20-FBIH / Development / Technical Assistance for EE Revolving fund /Policy & Regulatory Expert | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Limited | Signed | Cleared | 2020/05/10 | 2020/07/23 | [6 empty] | 2020/05/15 | 2020/09/09 | 2020/06/20 | 2020/10/22 | 2020/06/20 | 2020/10/18 | 2020/06/22 | 2020/10/22 |  | 2024/04/22
P143580-BA-BEEP-5393BA-IC-CS-15-25-RS / ACCOUNTANT AND DISBURSEMENT SPECIALIST | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Signed | Cleared | [11 empty] | 2015/06/18 |  |  |  | 2015/08/01
BEEPAF-P165405-IC-05-CS-20-FBIH / Technical Expert II | No | IBRD-89060 | Project Management | Prior | Consultant Services | Direct | Signed | Cleared | 2020/05/10 | 2020/06/04 |  |  |  |  | 2020/05/15 | 2020/06/04 | 2020/05/23 | 2020/06/04 | 2020/06/06 | 2020/06/08 | 2020/06/06 | 2020/06/16 | 2020/06/08 | 2020/06/09 |  | 2024/05/01
BEEPAF-P165405-IC-04-CS-20-FBIH / Technical Expert I | No | IBRD-89060 | Project Management | Prior | Consultant Services | Direct | Signed | Cleared | 2020/05/10 | 2020/06/04 |  |  |  |  | 2020/05/15 | 2020/06/04 | 2020/05/23 | 2020/06/04 | 2020/06/06 | 2020/06/08 | 2020/06/06 | 2020/06/16 | 2020/06/08 | 2020/06/09 |  | 2024/05/01
BEEPAF-P165405-IC-16-CS-20-FBIH / Development / Technical Assistance for EE Revolving fund / Revolving Fund Expert | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Limited | Signed | Cleared | 2020/05/10 | 2020/06/09 | [6 empty] | 2020/05/15 | 2020/09/09 | 2020/06/20 | 2020/10/22 | 2020/06/20 | 2020/10/18 | 2020/06/22 | 2020/10/22 |  | 2024/04/22
BEEP-P143580-IC-24-CS-14-FBIH / FOR PROJECT COORDINATOR (PC) IN THE IMPLEMENTATION UNIT OF THE FEDERATION MINISTRY OF PHYSICAL PLANNING | No | IDA-53930 | Energy Efficiency Investments in Public Facilities,Support for the Development of Scalable Financing Mechanisms and Capacity Building,Project Management | Prior | Consultant Services | Open | Terminated | Cleared | [11 empty] | 2015/11/28 |  |  |  | 2015/12/16
BEEPAF-P165405-IC-07-CS-20-FBIH / Contract Management Expert | No | IBRD-89060 | Project Management | Post | Consultant Services | Limited | Signed | Cleared | 2020/05/01 | 2020/02/21 | [6 empty] | 2020/05/01 | 2020/05/08 | 2020/06/06 | 2020/05/18 | 2020/06/06 | 2020/05/18 | 2020/06/08 | 2020/05/18 |  | 2024/05/01
BEEPAF-P165405-IC-21-CS-23-FBIH / Provision of services related to the diversifying funding sources for financing improvements in public sector buildings in Federation of Bosnia and Herzegovina | No | IBRD-89060 | Support for the Development of Scalable Financing Mechanisms and Capacity Building | Post | Consultant Services | Limited | Pending Implementation | Cleared | 2023-05-23 | [7 empty] | 2023-05-28 |  | 2023-06-07 |  | 2023-06-10 |  | 2023-06-13 |  |  | 2023-12-10